## Sheet1
Id | Description of Risk | Impact on Council | Assessment of | Assessment of | Grade (combined Likelihood and Seriousness) | Change | Date of Review | Mitigation Actions | Responsibility for mitigation action(s) | Cost | Timeline for mitigation action(s) | Work Breakdown Structure
| (including any identified ‘triggers’) | (Identify consequences [1]) | Likelihood | Seriousness |  |  |  | (Preventative or Contingency)
Insurance
Ins1 | Damage to third party property or individuals |  | L | M | D |  | Annual | Annual insurance renal for items stored on behalf of the Parish Council.
Ins2 | Council Property |  | L | M | D |  | Annual | Annual insurance renewal for property owned and or where by items are stored by other public or council memebrs suitable insurance is sought.
Ins3 | Public events |  | L | H | C |  | Annual | Suitable public liability insurance obtained before any special events. | Event Organiser | 99 | To be in place prior to event taking place.
Ins4 | Electrical Equipment | Damange to third party or property if inappropriuately used | L | M | D | Renting Generators for future events covers liability issues. | Annual | Annual PAT Testing to be completed and certificates issued for each item over 12 months old or out of manufacturs warranty
Ins5 | Gas Equipment | Damange to third party or property if inappropriuately used | L | M | D |  | Annual | Annual Gas Safety inspection to be completed and certificates issued for each item over 12 months old or out of manufacturs warranty
Ins6 | Insolvency of insurance company |  | L | M | D |  | Annual | Insure with large repultable insurance compnay only.
Ins7 | Loss through theft or dishonesty |  | L | M | D |  | Annual | Suitable insurance for items stored for the Parish Council
Ins8 | Personal Accident to officers of councillors |  | L | L | N |  | Annual | Suitbale personal liability insuance
Outside Influences
Out1 | Change to legislation |  | L | L | N |  |  | Advice received from relevant bodies; Full Council to provide effective training to Officers, Wardens and Councillors
Out2 | Contractors working on council property |  | L | M | D |  |  | Relevant insurance papers requested as part of contracting with 3rd party.
Management
Mgt1 | Officers working alone |  | L | L | N |  |  | Notifications to be made to other council memebrs of any lone working activities.
Mgt2 | Workers safety |  | L | M | D |  |  | First Aid certificates for those who work on site of Parish Properties.Or to be supervised with support of first aider.
Mgt 3 | Register of Interest |  | L | L | N |  |  | Register set up on website and maintained, annual or elctrol check made.
Mgt4 | Gift or Hospitality |  | L | L | N |  |  | All gifts and or hospitality over £25 is registered appropriately.
Mgt5 | Financial Records |  | L | L | N |  |  | Internal Audit completed twice yearly.
Mgt6 | Banking Arrangements |  | L | L | N |  |  | Internal Audit completed twice yearly.
Mgt7 | Computer, website & Emails |  | L | L | N |  |  | No computers owned by PC Website managed by others and emails hosted independatnlty.
Mgt8 | Precept |  | L | L | N |  |  | Annual review
Mgt9 | Meetings and Minutes |  | L | L | N |  |  | Agendas published in timely maner and minutes accurately reflec the meeting contact and published in accorance with the publised timescales.
Rating for Likelihood and Seriousness for each risk
L | Rated as Low | E | Rated as Extreme (Used for Seriousness only)
M | Rated as Medium | NA | Not Assessed
H | Rated as High
Grade: Combined effect of Likelihood/Seriousness
Seriousness
Likelihood |  | low | medium | high | EXTREME
| low | N | D | C | A
| medium | D | C | B | A
| high | C | B | A | A
Recommended actions for grades of risk
Grade | Risk mitigation actions
A | Mitigation actions, to reduce the likelihood and seriousness, to be identified and implemented as soon as the council commences as a priority.
B | Mitigation actions, to reduce the likelihood and seriousness, to be identified and appropriate actions implemented during council execution.
C | Mitigation actions, to reduce the likelihood and seriousness, to be identified and costed for possible action if funds permit.
D | To be noted - no action is needed unless grading increases over time.
N | To be noted - no action is needed unless grading increases over time.
Change to Grade since last assessment
NEW | New risk | ¯ | Grading decreased
— | No change to Grade | ­ | Grading increased